## P52100002646
| MahaRERA Project / Agent Registration Number | P51800008478
Sr No. | Project Name | Promoter Name | Last Modified Date | View Details | View Application | View Certificate | View Extension Certificate | View on Map | Directions
1 | Life Republic Sector R1 - 1st Avenue | KOLTE-PATIL INTEGRATED TOWNSHIPS LIMITED | 2022-04-18 | [Info in sheets besides] | <View Application> | <View Certificate> | <View Certificate (dim if not applicable)> | (not functional) | Link

## Organization
MahaRERA Application | Past Experience Details
General Information | Sr.No. | Project Name | Type of Project | Others | Land Area(In Sq mtrs) | Address | CTS Number | Number of Buildings/Plot | Number of Apartments | Original Proposed Date of Completion | Actual Date of Completion
| 1 | Life Republic Sector R2 Phase I | Residential | NA | 42116.81 | Marunji Hinjewadi Pune | 74P, 110P, 107P, 114P | 120 | 120 | 2013-12-31 | 2013-12-10
Information Type | 2 | Life Republic Sector R4 | Residential | NA | 33676.96 | Marunji Hinjewadi Pune | 112P, 113P, 115P, 117, 118, 120P | 5 | 660 | 2015-12-31 | 2016-12-03
Other Than Individual
Member Information
Organization
|  | Member Name | Designation | Photo
Name |  | RAHUL YASHAVANT TALELE | Authorized Signatory | View Photo
KOLTE-PATIL INTEGRATED TOWNSHIPS LIMITED
Organization Type
Company
Description For Other Type Organization
NA
Do you have any Past Experience ?
Yes
Address Details
Block Number
SURVEY NO 74
Building Name
MARUNJI
Street Name
MARUNJI-HINJEWADI-KARSAI ROAD
Locality
TALUKA MULSHI
Land mark
MARUNJI GAVTHAN
State/UT
MAHARASHTRA
Division
Pune
District
Pune
Taluka
Mulshi
Village
Hinjavadi (CT)
Pin Code
411057
Organization Contact Details
Office Number
2066778800
Website URL

## Project
Project
Project Name (Mention as per Sanctioned Plan)
Life Republic Sector R1 - 1st Avenue
Project Status
On-Going Project
Proposed Date of Completion
2026-12-31
Revised Proposed Date of Completion
2027-12-30
Litigations related to the project ?
Yes
Project Type
Residential
Are there any Promoter(Land Owner/ Investor) (as defined by MahaRERA Order) in the project ?
No
Plot Bearing No / CTS no / Survey Number/Final Plot no.
74 PART, 113 PART, 114 PART
Boundaries East
24 MTR WIDE TOWNSHIP INTERNAL ROAD
Boundaries West
TOWNSHIP BOUNDARY S NO 74 PART S NO 115 PART
Boundaries North
18 MTR WIDE TOWNSHIP INTERNAL ROAD
Boundaries South
12 MTR WIDE TOWNSHIP INTERNAL ROAD
State/UT
MAHARASHTRA
Division
Pune
District
Pune
Taluka
Mulshi
Village
Marunji
Street
Locality
Pin Code
411057
Total Plot/Project area (sqmts)
43543.41
Total Number of Proposed Building/Wings (In the Layout/Plot)
9
Is project plan sanctioned by MCGM?
Number of Sanctioned Building out of Above Proposed Count Applied for this Registration
9
Proposed But Not Sanctioned Buildings Count
0
Total Recreational Open Space as Per Sanctioned Plan
4384.12
FSI Details
Built-up-Area as per Proposed FSI (In sqmts) ( Proposed but not sanctioned) ( As soon as approved, should be immediately updated in Approved FSI)
0
Permissible Total FSI of Plot (Permissible Built-up Area)
115132.93
Out of the Above Sanctioned FSI (Sanctioned Built-up Area)
115132.93
Bank Details
Bank Name
INDUSIND BANK LIMITED
IFSC Code
INDB0000843

## Project Details
Project Details
Name | Proposed | Booked | WorkDone(In %)
Number of Garages ( In Numbers) | NA | NA | 0
Covered Parking ( In Numbers) | 1057 | 0 | 0
Development Work
Common areas And Facilities, Amenities | Available | Percent | Details
Internal Roads & Footpaths : | YES | 60 | work in progress
Water Conservation, Rain water Harvesting : | YES | 40 | work in progress
Energy management : | YES | 0 | Work yet to be started
Fire Protection And Fire Safety Requirements : | YES | 75 | work in progress
Electrical Meter Room, Sub-Station, Receiving Station : | YES | 100 | work in progress
Aggregate area of recreational Open Space : | YES | 75 | work in progress
Open Parking : | YES | 0 | Work yet to be started
Water Supply : | YES | 80 | work in progress
Sewerage (Chamber, Lines, Septic Tank , STP) : | YES | 80 | work in progress
Storm Water Drains : | YES | 80 | work in progress
Landscaping & Tree Planting : | YES | 50 | Work in progress
Street Lighting : | YES | 40 | Work in progress
Community Buildings : | YES | 100 | completed
Treatment And Disposal Of Sewage And Sullage Water : | YES | 95 | work in progress
Solid Waste Management And Disposal : | YES | 95 | work in progress
Building Details
Sr.No. | Project Name | Name (Also mention identification of building/wing/other as per approved plan) | Proposed Date of Completion | Number of Basement's | Number of Plinth | Number of Podium's | Number of Sanctioned Floors | Number of Stilts | Total no. of open Parking as per Sanctioned Plan (4-wheeler+2-Wheeler) | Number of Closed Parking
1 | Life Republic Sector R1 - 1st Avenue | A | 2021-12-31 | 0 | 1 | 0 | 22 | 1 | 20 | 34
|  | Sr.No. | Apartment Type | Carpet Area (in Sqmts) | Number of Apartment | Number of Booked Apartment
|  | 1 | 2 BHK | 58.64 | 22 | 22
|  | 2 | 3 BHK | 81.32 | 22 | 22
|  | 3 | 2 BHK | 57.45 | 22 | 22
|  | 4 | 2 BHK | 58.07 | 22 | 22
|  | 5 | 2 BHK | 56.88 | 22 | 22
|  | 6 | 3 BHK | 80.06 | 22 | 21
|  | 7 | 3 BHK | 76.37 | 22 | 22
|  | 8 | 3 BHK | 77.64 | 22 | 18
|  | Sr.No. | Tasks / Activity | Percentage of Work
|  | 1 | Excavation | 100
|  | 2 | X number of Basement(s) and Plinth | 100
|  | 3 | X number of Podiums | 0
|  | 4 | Stilt Floor | 100
|  | 5 | X number of Slabs of Super Structure | 100
|  | 6 | Internal walls, Internal Plaster, Floorings within Flats/Premises, Doors and Windows to each of the Flat/Premises | 100
|  | 7 | Sanitary Fittings within the Flat/Premises,Electrical Fittings within the Flat/Premises | 100
|  | 8 | Staircases, Lifts Wells and Lobbies at each Floor level connecting Staircases and Lifts, Overhead and Underground Water Tanks. | 100
|  | 9 | The external plumbing and external plaster, elevation, completion of terraces with waterproofing of the Building/Wing | 100
|  | 10 | Installation of lifts, water pumps, Fire Fighting Fittings and Equipment as per CFO NOC, Electrical fittings to Common Areas, electro, mechanical equipment, Compliance to conditions of environment /CRZ NOC, Finishing to entrance lobby/s, plinth protection, paving of areas appurtenant to Building/Wing, Compound Wall and all other requirements as may be required to Obtain Occupation /Completion Certificate | 100
Sr.No. | Project Name | Name (Also mention identification of building/wing/other as per approved plan) | Proposed Date of Completion | Number of Basement's | Number of Plinth | Number of Podium's | Number of Sanctioned Floors | Number of Stilts | Total no. of open Parking as per Sanctioned Plan (4-wheeler+2-Wheeler) | Number of Closed Parking
2 | Life Republic Sector R1 - 1st Avenue | B | 2022-12-31 | 0 | 1 | 0 | 22 | 1 | 20 | 34
|  | Sr.No. | Apartment Type | Carpet Area (in Sqmts) | Number of Apartment | Number of Booked Apartment
|  | 1 | 2 BHK | 57.58 | 44 | 42
|  | 2 | 2 BHK | 57.19 | 44 | 42
|  | 3 | 3 BHK | 76.37 | 44 | 42
|  | 4 | 3 BHK | 77.61 | 44 | 42
|  | Sr.No. | Tasks / Activity | Percentage of Work
|  | 1 | Excavation | 100
|  | 2 | X number of Basement(s) and Plinth | 100
|  | 3 | X number of Podiums | 0
|  | 4 | Stilt Floor | 100
|  | 5 | X number of Slabs of Super Structure | 100
|  | 6 | Internal walls, Internal Plaster, Floorings within Flats/Premises, Doors and Windows to each of the Flat/Premises | 60
|  | 7 | Sanitary Fittings within the Flat/Premises,Electrical Fittings within the Flat/Premises | 0
|  | 8 | Staircases, Lifts Wells and Lobbies at each Floor level connecting Staircases and Lifts, Overhead and Underground Water Tanks. | 0
|  | 9 | The external plumbing and external plaster, elevation, completion of terraces with waterproofing of the Building/Wing | 90
|  | 10 | Installation of lifts, water pumps, Fire Fighting Fittings and Equipment as per CFO NOC, Electrical fittings to Common Areas, electro, mechanical equipment, Compliance to conditions of environment /CRZ NOC, Finishing to entrance lobby/s, plinth protection, paving of areas appurtenant to Building/Wing, Compound Wall and all other requirements as may be required to Obtain Occupation /Completion Certificate | 30
Sr.No. | Project Name | Name (Also mention identification of building/wing/other as per approved plan) | Proposed Date of Completion | Number of Basement's | Number of Plinth | Number of Podium's | Number of Sanctioned Floors | Number of Stilts | Total no. of open Parking as per Sanctioned Plan (4-wheeler+2-Wheeler) | Number of Closed Parking
3 | Life Republic Sector R1 - 1st Avenue | C | 2025-10-31 | 0 | 1 | 0 | 23 | 1 | 22 | 154
|  | Sr.No. | Apartment Type | Carpet Area (in Sqmts) | Number of Apartment | Number of Booked Apartment
|  | 1 | 3 RLK | 70.87 | 85 | 28
|  | 2 | 3 RLK | 69.83 | 88 | 3
|  | Sr.No. | Tasks / Activity | Percentage of Work
|  | 1 | Excavation | 100
|  | 2 | X number of Basement(s) and Plinth | 0
|  | 3 | X number of Podiums | 0
|  | 4 | Stilt Floor | 0
|  | 5 | X number of Slabs of Super Structure | 0
|  | 6 | Internal walls, Internal Plaster, Floorings within Flats/Premises, Doors and Windows to each of the Flat/Premises | 0
|  | 7 | Sanitary Fittings within the Flat/Premises,Electrical Fittings within the Flat/Premises | 0
|  | 8 | Staircases, Lifts Wells and Lobbies at each Floor level connecting Staircases and Lifts, Overhead and Underground Water Tanks. | 0
|  | 9 | The external plumbing and external plaster, elevation, completion of terraces with waterproofing of the Building/Wing | 0
|  | 10 | Installation of lifts, water pumps, Fire Fighting Fittings and Equipment as per CFO NOC, Electrical fittings to Common Areas, electro, mechanical equipment, Compliance to conditions of environment /CRZ NOC, Finishing to entrance lobby/s, plinth protection, paving of areas appurtenant to Building/Wing, Compound Wall and all other requirements as may be required to Obtain Occupation /Completion Certificate | 0
Sr.No. | Project Name | Name (Also mention identification of building/wing/other as per approved plan) | Proposed Date of Completion | Number of Basement's | Number of Plinth | Number of Podium's | Number of Sanctioned Floors | Number of Stilts | Total no. of open Parking as per Sanctioned Plan (4-wheeler+2-Wheeler) | Number of Closed Parking
4 | Life Republic Sector R1 - 1st Avenue | D | 2026-12-31 | 0 | 1 | 0 | 22 | 1 | 20 | 34
|  | Sr.No. | Apartment Type | Carpet Area (in Sqmts) | Number of Apartment | Number of Booked Apartment
|  | 1 | 2 BHK | 58.64 | 22 | 0
|  | 2 | 2 BHK | 57.45 | 22 | 0
|  | 3 | 2 BHK | 58.07 | 22 | 0
|  | 4 | 2 BHK | 56.88 | 22 | 0
|  | 5 | 3 BHK | 80.06 | 22 | 0
|  | 6 | 3 BHK | 76.37 | 22 | 0
|  | 7 | 3 BHK | 81.32 | 22 | 0
|  | 8 | 3 BHK | 77.64 | 22 | 0
|  | Sr.No. | Tasks / Activity | Percentage of Work
|  | 1 | Excavation | 0
|  | 2 | X number of Basement(s) and Plinth | 0
|  | 3 | X number of Podiums | 0
|  | 4 | Stilt Floor | 0
|  | 5 | X number of Slabs of Super Structure | 0
|  | 6 | Internal walls, Internal Plaster, Floorings within Flats/Premises, Doors and Windows to each of the Flat/Premises | 0
|  | 7 | Sanitary Fittings within the Flat/Premises,Electrical Fittings within the Flat/Premises | 0
|  | 8 | Staircases, Lifts Wells and Lobbies at each Floor level connecting Staircases and Lifts, Overhead and Underground Water Tanks. | 0
|  | 9 | The external plumbing and external plaster, elevation, completion of terraces with waterproofing of the Building/Wing | 0
|  | 10 | Installation of lifts, water pumps, Fire Fighting Fittings and Equipment as per CFO NOC, Electrical fittings to Common Areas, electro, mechanical equipment, Compliance to conditions of environment /CRZ NOC, Finishing to entrance lobby/s, plinth protection, paving of areas appurtenant to Building/Wing, Compound Wall and all other requirements as may be required to Obtain Occupation /Completion Certificate | 0
Sr.No. | Project Name | Name (Also mention identification of building/wing/other as per approved plan) | Proposed Date of Completion | Number of Basement's | Number of Plinth | Number of Podium's | Number of Sanctioned Floors | Number of Stilts | Total no. of open Parking as per Sanctioned Plan (4-wheeler+2-Wheeler) | Number of Closed Parking
5 | Life Republic Sector R1 - 1st Avenue | E | 2022-12-31 | 0 | 1 | 0 | 22 | 1 | 20 | 27
|  | Sr.No. | Apartment Type | Carpet Area (in Sqmts) | Number of Apartment | Number of Booked Apartment
|  | 1 | 2 BHK | 58.07 | 44 | 40
|  | 2 | 2 BHK | 55.84 | 44 | 42
|  | 3 | 2 BHK | 57.44 | 44 | 43
|  | 4 | 2 BHK | 56.47 | 44 | 40
|  | Sr.No. | Tasks / Activity | Percentage of Work
|  | 1 | Excavation | 100
|  | 2 | X number of Basement(s) and Plinth | 100
|  | 3 | X number of Podiums | 0
|  | 4 | Stilt Floor | 100
|  | 5 | X number of Slabs of Super Structure | 100
|  | 6 | Internal walls, Internal Plaster, Floorings within Flats/Premises, Doors and Windows to each of the Flat/Premises | 70
|  | 7 | Sanitary Fittings within the Flat/Premises,Electrical Fittings within the Flat/Premises | 0
|  | 8 | Staircases, Lifts Wells and Lobbies at each Floor level connecting Staircases and Lifts, Overhead and Underground Water Tanks. | 0
|  | 9 | The external plumbing and external plaster, elevation, completion of terraces with waterproofing of the Building/Wing | 90
|  | 10 | Installation of lifts, water pumps, Fire Fighting Fittings and Equipment as per CFO NOC, Electrical fittings to Common Areas, electro, mechanical equipment, Compliance to conditions of environment /CRZ NOC, Finishing to entrance lobby/s, plinth protection, paving of areas appurtenant to Building/Wing, Compound Wall and all other requirements as may be required to Obtain Occupation /Completion Certificate | 30
Sr.No. | Project Name | Name (Also mention identification of building/wing/other as per approved plan) | Proposed Date of Completion | Number of Basement's | Number of Plinth | Number of Podium's | Number of Sanctioned Floors | Number of Stilts | Total no. of open Parking as per Sanctioned Plan (4-wheeler+2-Wheeler) | Number of Closed Parking
6 | Life Republic Sector R1 - 1st Avenue | F | 2022-12-31 | 0 | 1 | 0 | 22 | 1 | 21 | 27
|  | Sr.No. | Apartment Type | Carpet Area (in Sqmts) | Number of Apartment | Number of Booked Apartment
|  | 1 | 2 BHK | 56.43 | 44 | 41
|  | 2 | 2 BHK | 56.58 | 44 | 42
|  | 3 | 2 BHK | 55.92 | 88 | 80
|  | Sr.No. | Tasks / Activity | Percentage of Work
|  | 1 | Excavation | 100
|  | 2 | X number of Basement(s) and Plinth | 100
|  | 3 | X number of Podiums | 0
|  | 4 | Stilt Floor | 100
|  | 5 | X number of Slabs of Super Structure | 100
|  | 6 | Internal walls, Internal Plaster, Floorings within Flats/Premises, Doors and Windows to each of the Flat/Premises | 70
|  | 7 | Sanitary Fittings within the Flat/Premises,Electrical Fittings within the Flat/Premises | 0
|  | 8 | Staircases, Lifts Wells and Lobbies at each Floor level connecting Staircases and Lifts, Overhead and Underground Water Tanks. | 0
|  | 9 | The external plumbing and external plaster, elevation, completion of terraces with waterproofing of the Building/Wing | 90
|  | 10 | Installation of lifts, water pumps, Fire Fighting Fittings and Equipment as per CFO NOC, Electrical fittings to Common Areas, electro, mechanical equipment, Compliance to conditions of environment /CRZ NOC, Finishing to entrance lobby/s, plinth protection, paving of areas appurtenant to Building/Wing, Compound Wall and all other requirements as may be required to Obtain Occupation /Completion Certificate | 30
Sr.No. | Project Name | Name (Also mention identification of building/wing/other as per approved plan) | Proposed Date of Completion | Number of Basement's | Number of Plinth | Number of Podium's | Number of Sanctioned Floors | Number of Stilts | Total no. of open Parking as per Sanctioned Plan (4-wheeler+2-Wheeler) | Number of Closed Parking
7 | Life Republic Sector R1 - 1st Avenue | G | 2021-12-31 | 0 | 1 | 0 | 22 | 1 | 21 | 27
|  | Sr.No. | Apartment Type | Carpet Area (in Sqmts) | Number of Apartment | Number of Booked Apartment
|  | 1 | 2 BHK | 56.58 | 44 | 44
|  | 2 | 2 BHK | 56.43 | 44 | 44
|  | 3 | 2 BHK | 55.92 | 88 | 87
|  | Sr.No. | Tasks / Activity | Percentage of Work
|  | 1 | Excavation | 100
|  | 2 | X number of Basement(s) and Plinth | 100
|  | 3 | X number of Podiums | 0
|  | 4 | Stilt Floor | 100
|  | 5 | X number of Slabs of Super Structure | 100
|  | 6 | Internal walls, Internal Plaster, Floorings within Flats/Premises, Doors and Windows to each of the Flat/Premises | 100
|  | 7 | Sanitary Fittings within the Flat/Premises,Electrical Fittings within the Flat/Premises | 100
|  | 8 | Staircases, Lifts Wells and Lobbies at each Floor level connecting Staircases and Lifts, Overhead and Underground Water Tanks. | 100
|  | 9 | The external plumbing and external plaster, elevation, completion of terraces with waterproofing of the Building/Wing | 100
|  | 10 | Installation of lifts, water pumps, Fire Fighting Fittings and Equipment as per CFO NOC, Electrical fittings to Common Areas, electro, mechanical equipment, Compliance to conditions of environment /CRZ NOC, Finishing to entrance lobby/s, plinth protection, paving of areas appurtenant to Building/Wing, Compound Wall and all other requirements as may be required to Obtain Occupation /Completion Certificate | 100
Sr.No. | Project Name | Name (Also mention identification of building/wing/other as per approved plan) | Proposed Date of Completion | Number of Basement's | Number of Plinth | Number of Podium's | Number of Sanctioned Floors | Number of Stilts | Total no. of open Parking as per Sanctioned Plan (4-wheeler+2-Wheeler) | Number of Closed Parking
8 | Life Republic Sector R1 - 1st Avenue | Parking 1 |  | 0 | 1 | 0 | 1 | 0 | 0 | 47
|  | Sr.No. | Apartment Type | Carpet Area (in Sqmts) | Number of Apartment | Number of Booked Apartment
|  | 1 | Parking Building | 0 | 0 | 0
|  | Sr.No. | Tasks / Activity | Percentage of Work
|  | 1 | Excavation | 100
|  | 2 | X number of Basement(s) and Plinth | 100
|  | 3 | X number of Podiums | 0
|  | 4 | Stilt Floor | 0
|  | 5 | X number of Slabs of Super Structure | 100
|  | 6 | Internal walls, Internal Plaster, Floorings within Flats/Premises, Doors and Windows to each of the Flat/Premises | 90
|  | 7 | Sanitary Fittings within the Flat/Premises,Electrical Fittings within the Flat/Premises | 75
|  | 8 | Staircases, Lifts Wells and Lobbies at each Floor level connecting Staircases and Lifts, Overhead and Underground Water Tanks. | 75
|  | 9 | The external plumbing and external plaster, elevation, completion of terraces with waterproofing of the Building/Wing | 75
|  | 10 | Installation of lifts, water pumps, Fire Fighting Fittings and Equipment as per CFO NOC, Electrical fittings to Common Areas, electro, mechanical equipment, Compliance to conditions of environment /CRZ NOC, Finishing to entrance lobby/s, plinth protection, paving of areas appurtenant to Building/Wing, Compound Wall and all other requirements as may be required to Obtain Occupation /Completion Certificate | 75
Sr.No. | Project Name | Name (Also mention identification of building/wing/other as per approved plan) | Proposed Date of Completion | Number of Basement's | Number of Plinth | Number of Podium's | Number of Sanctioned Floors | Number of Stilts | Total no. of open Parking as per Sanctioned Plan (4-wheeler+2-Wheeler) | Number of Closed Parking
9 | Life Republic Sector R1 - 1st Avenue | Parking 2 |  | 0 | 1 | 0 | 4 | 0 | 0 | 793
|  | Sr.No. | Apartment Type | Carpet Area (in Sqmts) | Number of Apartment | Number of Booked Apartment
|  | 1 | Parking Building | 0 | 0 | 0
|  | Sr.No. | Tasks / Activity | Percentage of Work
|  | 1 | Excavation | 100
|  | 2 | X number of Basement(s) and Plinth | 100
|  | 3 | X number of Podiums | 0
|  | 4 | Stilt Floor | 0
|  | 5 | X number of Slabs of Super Structure | 100
|  | 6 | Internal walls, Internal Plaster, Floorings within Flats/Premises, Doors and Windows to each of the Flat/Premises | 100
|  | 7 | Sanitary Fittings within the Flat/Premises,Electrical Fittings within the Flat/Premises | 100
|  | 8 | Staircases, Lifts Wells and Lobbies at each Floor level connecting Staircases and Lifts, Overhead and Underground Water Tanks. | 0
|  | 9 | The external plumbing and external plaster, elevation, completion of terraces with waterproofing of the Building/Wing | 100
|  | 10 | Installation of lifts, water pumps, Fire Fighting Fittings and Equipment as per CFO NOC, Electrical fittings to Common Areas, electro, mechanical equipment, Compliance to conditions of environment /CRZ NOC, Finishing to entrance lobby/s, plinth protection, paving of areas appurtenant to Building/Wing, Compound Wall and all other requirements as may be required to Obtain Occupation /Completion Certificate | 0
Project Professional Information
Professional Name | MahaRERA Certificate No. | Professional Type
SPACE DESIGNERS’ SYNDICATE | NA | Architect
JW Consultants LLP | NA | Engineer
360 REALTORS LLP | A51900000246 | Real Estate Agent
AMIT BABANRAO GAIKI | A52100002350 | Real Estate Agent
AMIT VINODKUMAR GUPTA | A52100000529 | Real Estate Agent
BAJAJ FINANCE LTD | A52100003465 | Real Estate Agent
FULL BASKET PROPERTY SERVICES PRIVATE LIMITED | A52100005036 | Real Estate Agent
LIFE SPACE PROPERTY SOLUTIONS PVT LTD | A52100000993 | Real Estate Agent
LivingArea | A52100006453 | Real Estate Agent
Nimbleland Infracon LLP | A52100004080 | Real Estate Agent
Pin Click Property Management Pvt Ltd. | A52100012083 | Real Estate Agent
REPUBLICOF PROPERTY PRIVATE LIMITED | A52100012323 | Real Estate Agent
SPACEINDIA NEST LLP | A52100002248 | Real Estate Agent
PROPINN PROPERTIES PRIVATE LIMITED | A52100011114 | Real Estate Agent
CORAZON HOMES AND SECURITIES | A52100000096 | Real Estate Agent
MADAN MOHAN AGARWAL | A52100002429 | Real Estate Agent
Prasad Bhaskar Yede | A52100004531 | Real Estate Agent
KAMAL DHARAMDAS BULANI | A52100000533 | Real Estate Agent
CORAZON HOMES AND SECURITIES | A52100000096 | Real Estate Agent
Mukundi Lal Vishwakarma | A52100003071 | Real Estate Agent
Ketaki Zagade | A52100003506 | Real Estate Agent
DREAMZ REALTY CONCEPT | A51900005334 | Real Estate Agent
Jakir Anvarali Sahikh | A52100010993 | Real Estate Agent
FANM Property Services Pvt Ltd | A52000000045 | Real Estate Agent
Premlata Estate Solutions Pvt. Ltd. | A52100000033 | Real Estate Agent
GLOBAL REALTORS | A52100000018 | Real Estate Agent
HomeAdda | A52100001337 | Real Estate Agent
India e Hub Services Pvt Ltd | A52100011365 | Real Estate Agent
Amit Kumar Das | A52100007168 | Real Estate Agent
NITESH KUMAR SINGH | A52100002854 | Real Estate Agent
chirag brijpuria | A52100007920 | Real Estate Agent
Namo Properties | A52100014539 | Real Estate Agent
PRIYA VIKRAM GHORPADE | A52100002387 | Real Estate Agent
VISHWA DEEPAK PANDEY | A52100006029 | Real Estate Agent
VITTHAL CHANDARRAO KASALE | A52100009918 | Real Estate Agent
PROPENGINE REALTECH LLP | A52100000628 | Real Estate Agent
Vineet Arun Singh | A52100012069 | Real Estate Agent
Sumit Khatri | A52100003156 | Real Estate Agent
Vikas Pralhad Yewle | A52100000151 | Real Estate Agent
RANJEET SINGH YADAV | A52100000402 | Real Estate Agent
ELARA MARKETING SERVICES PRIVATE LIMITED | A51700000030 | Real Estate Agent
MOHSIN ABDUL KHAN | A52100009864 | Real Estate Agent
KPRBSK REALTORS PRIVATE LIMITED | A52100012415 | Real Estate Agent
SQUARE YARDS CONSULTING PRIVATE LIMITED | A51800000454 | Real Estate Agent
Salman Mansoor Shaikh | A52100002502 | Real Estate Agent
Atul Ramchandra Mazire | A52100000560 | Real Estate Agent
PRASAD KRISHNA GHORPADE | A52100003639 | Real Estate Agent
WISTERIA REAL VISION PVT LTD | A52100003089 | Real Estate Agent
HDFC Realty Limited | A51900000107 | Real Estate Agent
NITIN SHANKAR KADDE | A52100000577 | Real Estate Agent
CBRE South Asia Private Limited | A51600003050 | Real Estate Agent
ANAROCK Property Consultants Pvt. Ltd. | A51900000108 | Real Estate Agent
AMBITUS REALTORS AND ADVISORS PRIVATE LIMITED | A52100009541 | Real Estate Agent
Chirag Vinayak Shah | A51900000517 | Real Estate Agent
Manan Rohit Raja | A52100003147 | Real Estate Agent
SMC REAL ESTATE ADVISORS PRIVATE LIMITED | A51900000042 | Real Estate Agent
Litigations Details
Project Name | Court Name | Case Number | Case Type | Preventive/Injunction/Interim Order is Passed? | Petition Name | Other Petition Details | Year | Present Status | Documents
Life Republic Sector R1 - 1st Avenue | CJJD | SPL CS No 265/2013 | Civil | No | Suit |  | 2013 | The matter is pending adjudication and is pending at evidence stage | NA
Life Republic Sector R1 - 1st Avenue | CJJD | RCS No 1487/2005 | Civil | No | Suit |  | 2005 | The matter is pending adjudication and is currently fixed for evidence | NA
Life Republic Sector R1 - 1st Avenue | CJSD | SPL CS 2255/2009 | Civil | No | Suit |  | 2009 | The matter is pending adjudication and is currently fixed for framing additional issues | NA
Life Republic Sector R1 - 1st Avenue | CJSD | SPL CS 575/2015 | Civil | No | Suit |  | 2015 | Framing of issues by honourable court | NA
Life Republic Sector R1 - 1st Avenue | Supreme Court | SLP CC No 9467/2017 | Civil | No | Suit |  | 2017 | Currently the matter is pending for final argument | NA
Life Republic Sector R1 - 1st Avenue | CJSD Pune | Civil MA 372/2022 | Civil | No | Suit |  | 2022 | Appearance and Filing of Say | NA
Life Republic Sector R1 - 1st Avenue | Supreme Court | SLP C CC No 9463/2017 | Civil | No | Suit |  | 2017 | Currently the matter is pending for final argument | NA
Life Republic Sector R1 - 1st Avenue | CJSD Pune | 421/2016 | Civil | No | Suit |  | 2016 | Currently the suit is pending for withdrawal or dismissal The plaintiff has filed withdrawal purshis | NA
Life Republic Sector R1 - 1st Avenue | High Court | 11697/2017 | Civil | No | Writ Petition |  | 2017 | Currently the matter is pending for admission | NA
Life Republic Sector R1 - 1st Avenue | High Court | 11701/2017 | Civil | No | Writ Petition |  | 2017 | Currently the matter is pending for admission | NA
Life Republic Sector R1 - 1st Avenue | High Court | 11702/2017 | Civil | No | Writ Petition |  | 2017 | Currently the matter is pending for admission | NA
Life Republic Sector R1 - 1st Avenue | CJJD | RCS 1689/2021 | Civil | No | Suit |  | 2021 | Currently the matter is posted for filing of written statement | NA
Life Republic Sector R1 - 1st Avenue | High Court | WPST 31252/2017 | Civil | No | Writ Petition |  | 2017 | The matter is yet to come up for hearing before court Current stage is pre admission for circulation | NA

## Uploaded Documents
Uploaded Documents
Document Name | Uploaded Document
1 Copy of the legal title report
1 Details of encumbrances
2 Details of encumbrances
3 Details of encumbrances
1 Copy of Layout Approval (in case of layout)
2 Copy of Layout Approval (in case of layout)
1 Building Plan Approval (IOD)
2 Building Plan Approval (IOD)
3 Building Plan Approval (IOD)
1 Commencement Certificates / NA Order for plotted development
2 Commencement Certificates / NA Order for plotted development
1 Declaration about Commencement Certificate
1 Declaration in FORM B
1 Certificates of Architect (Form 1)(Mandatory for only ongoing project)
2 Certificates of Architect (Form 1)(Mandatory for only ongoing project)
3 Certificates of Architect (Form 1)(Mandatory for only ongoing project)
1 Certificates of Engineer (Form 2)(Mandatory for only ongoing project)
2 Certificates of Engineer (Form 2)(Mandatory for only ongoing project)
3 Certificates of Engineer (Form 2)(Mandatory for only ongoing project)
1 CERSAI details
2 CERSAI details
1 Engineers Certificate on Quality Assurance (Form 2A FY 2019-20)
1 Disclosure of sold/ booked inventory
2 Disclosure of sold/ booked inventory
3 Disclosure of sold/ booked inventory
4 Disclosure of sold/ booked inventory
1 Certificates of CA (Form 5)
2 Certificates of CA (Form 5)
3 Certificates of CA (Form 5)
1 Engineers Certificate on Quality Assurance (Form 2A FY 2020-21)
1 Annual Audit Report of Statutory CA (Form 5) (FY 2018-19)
1 Annual Audit Report of Statutory CA (Form 5) (FY 2019-20)
1 Annual Audit Report of Statutory CA (Form 5) (FY 2020-21)
1 Proforma of the allotment letter and agreement for sale
2 Proforma of the allotment letter and agreement for sale
3 Proforma of the allotment letter and agreement for sale
4 Proforma of the allotment letter and agreement for sale
5 Proforma of the allotment letter and agreement for sale
6 Proforma of the allotment letter and agreement for sale
7 Proforma of the allotment letter and agreement for sale
8 Proforma of the allotment letter and agreement for sale
9 Proforma of the allotment letter and agreement for sale
10 Proforma of the allotment letter and agreement for sale
11 Proforma of the allotment letter and agreement for sale
12 Proforma of the allotment letter and agreement for sale
13 Proforma of the allotment letter and agreement for sale
14 Proforma of the allotment letter and agreement for sale
15 Proforma of the allotment letter and agreement for sale
16 Proforma of the allotment letter and agreement for sale
17 Proforma of the allotment letter and agreement for sale
18 Proforma of the allotment letter and agreement for sale
19 Proforma of the allotment letter and agreement for sale
20 Proforma of the allotment letter and agreement for sale
21 Proforma of the allotment letter and agreement for sale
1 Architect’s Certificate on Completion of Project (Form 4) | Not Uploaded
1 Status of Formation of Legal Entity (Society/Co Op etc.)
1 Status of Conveyance | Not Uploaded
1 Other | Not Uploaded